## Overview
NP - Grant Management - Proposal Template ( July 24 ) v2.5
PROPOSAL DETAILS
Proposal Title | Automotive Battery Thermal Runaway Prediction
Total Project Value ($) |  | Auto populate from Section 2 - Budget
Project Duration ( Months ) | 12
RIE2025 - Domains | Urban Solutions and Sustainability
EXTERNAL COLLABORATOR(S)
Company Name | UEN | Company Type | Contribution Cash $ | Contribution In-Kind $ | Remarks
Infineon Technologies |  | MNC | 0 |  | Provide microcontrollers and batteries
|  | Please select … | 0 | 0
|  | Please select … | 0 | 0
|  | Please select … | 0 | 0
* Relevant to NP Capability Development Grant
ABSTRACT
The rapid adoption of Lithium-ion batteries (LIBs) in electric vehicles is currently hindered by safety concerns, specifically the catastrophic failure mode known as thermal runaway. While Battery Management Systems (BMS) are effective at detecting failures as they occur, there is a critical need for prognostic capabilities that can predict thermal runaway events before the onset of irreversible heat generation. This project investigates the correlation between standard battery cycling parameters—voltage, current, and temperature—and the precursors to thermal runaway. By performing rigourous charge and discharge tests on batteries under unfavourable environmental conditions, experimental data will be generated by subjecting battery cells to accelerated aging cycles and abusive loading conditions to induce degradation. A time-series dataset will be analyzed to capture the electrochemical evolution of the cells leading up to failure. Using this dataset, a machine learning model can be developed to identify subtle non-linear anomalies in the voltage relaxation and internal resistance curves. These findings will be used to develop data-driven prognosis algorithms into existing BMS architectures, significantly enhancing operational safety by isolating at-risk cells before catastrophic failure occurs. | [5 empty] | 176 | Word Count
Background IP
As the objective of the RIE2025 grant is to develop commercial products, systems and applications using IP from the local universities, research institutes and Polytechnics and ITE, please be informed that applicants should not propose projects that use IPs created outside of Singapore.
NA | [5 empty] | 1 | Word Count
Background IP
If a company's background IP(s) is/are invovled, please provide the exact details. List down the patent reference number(s) if available.
N.A. | [5 empty] | 1 | Word Count
SCOPE OF PROJECT
The primary objective is to perform rigourous testing to gather datasets for development of a predictive model capable of identifying early warning signs (precursors) of thermal runaway in Lithium-ion cells before catastrophic failure occurs. The project will utilize controlled battery cycling to induce degradation and capture high-resolution electrochemical data for analysis. Experimental Setup & Safety Test Bench Construction: Setup of battery cyclers (Chroma & NGI) and environmental chambers. Sensor Integration: Installation of thermocouples, voltage sensors, and strain gauges (if monitoring swelling) on target cells. Safety Protocols: Implementation of containment vessels and fire suppression systems to manage intentional or accidental thermal events during testing. Data Generation (Cycling Regimes) Baseline Characterization: Performing initial capacity and impedance checks on fresh cells. Accelerated Aging: Subjecting cells to high C-rate cycling and elevated temperatures to speed up degradation. Abuse/Trigger Testing: Controlled overcharge or overheating protocols designed to push cells toward the "onset" of thermal runaway to capture near-failure data. Constraint: Testing will stop immediately upon detection of thermal runaway initiation (venting or rapid temp rise) to preserve data integrity. Data Analysis & Modeling Extracting key features from raw data, such as coulombic efficiency trends, differential voltage analysis, temperature rate of change, and using them to develop deep learning models for prediction. | [5 empty] | 197 | Word Count
References
[6 empty] | 1 | Word Count
PROJECT DELIVERABLES
1. Data Collection: Build a time-stamped CSV database of voltage, current, and temperature profiles for battery cells. 2. Data Processing: Clean, preprocess, and extract features for deep-learning model inputs. 3. Model Development: Train and compare predictive models and document model performance. 4. Hardware Integration: Compile and deploy the finalized models onto Infineon controller hardware for commercial EV use. 5. Final Report: Deliver a project report summarizing methods, results, and implementation. | [5 empty] | 66 | Word Count
~ End of Page ~

## Project Team - Timeline
NP - Grant Management - Proposal Template ( Oct'21 )
Section 3 - Project Team & Time Line
EXTERNAL COLLABORATOR(S)
Company name and type auto-populate from Section 1 - Overview For classification of Company Type, refer to NOTES page.
Company Name Auto-populate from Overview | Company Type Auto-populate from Overview | Salutation |  | Name |  |  | Designation |  |  | Area of Expertise | Collaborator Responsibility and project contribution
Infineon Technologies |  | Mr |  | Robert |  |  | System Architect
Infineon Technologies |  | Dr |  | Wesley Poh |  |  | AI Application Engineer
0 | 0 | Please select …
TIME LINE
Project - Intermediate Milestones |  | Year 1 |  |  |  | Year 2
|  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Battery Chamber and cycler setup. Equipment and software training | bar: Year 1 Q1
Testing phase and data generation | bar: Year 1 Q1 to Year 1 Q2
Data collection and processing | bar: Year 1 Q2 to Year 1 Q3
Model development and hardware integration | bar: Year 1 Q3 to Year 1 Q4
Collaborators - Intermediate Milestones |  | Year 1 Q1: Year 1; Year 2 Q1: Year 2
|  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Battery Chamber and cycler setup. Provide software training | bar: Year 1 Q1
Conduct testing and data generation | bar: Year 1 Q1 to Year 1 Q2
Processing of data | bar: Year 1 Q2 to Year 1 Q3
Model development and hardware integration | bar: Year 1 Q3 to Year 1 Q4
Students - Intermediate Milestones |  | Year 1 Q1: Year 1; Year 2 Q1: Year 2
|  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Undertake training on software and equipment operations | bar: Year 1 Q1
Conduct testing and data generation | bar: Year 1 Q1 to Year 1 Q2
Processing of data | bar: Year 1 Q2 to Year 1 Q3
Assist in model development. Prepare report deliverables | bar: Year 1 Q3 to Year 1 Q4
~ End of Page ~

## Project Info
NP - Grant Management - Proposal Template ( Oct'21 )
Section 4 - Project Information
What is the idea of the project about and it's impact and significance ?
The rapid adoption of Lithium-ion batteries (LIBs) in electric vehicles is currently hindered by safety concerns, specifically the catastrophic failure mode known as thermal runaway. While Battery Management Systems (BMS) are effective at detecting failures as they occur, there is a critical need for prognostic capabilities that can predict thermal runaway events before the onset of irreversible heat generation. This promotes battery safety in EVs and avoid catasrophic failures | 68 | Word Count
The Commercial Problem and Opportunity. What are the field of application ?
| 1 | Word Count
Users and Customers. Who are the potential licensees ?
Users includes industrial consumers, and battery manufacturers and automotive companies who manufactures EV energy storage | 15 | Word Count
What's your COMPETITIVE EDGES of your IDEA? - Describe your COMPETITIVE EDGES by identifying the key benefit and key differentiator. Compare them with your competitors.
Current Battery Monitoring Systems (BMS) in the market does not predict a thermal runaway. This idea provides the user a prediction on a thermal runaway and recommend replacement before catastrophic failure occurs. This promotes battery safety in the automotive and energy storage systems. | 43 | Word Count
Describe the Technology Readiness Level of the project before and after.
| 1 | Word Count
Who's on your TEAM? - Describe the strength of your team by referring to its skills, commitment and synergy.
Dr Wesley Poh specialized in Mr Robert Tan specialized in Dr Zhu Tai Xiu Mr Benjamin Wing Ms Jaseema Banu | 18 | Word Count
Describe the Novelty of your IDEA. Justify by IP and market scanning.
| 1 | Word Count
What's your PATH TO MARKET? - Describe your PATH TO MARKET by major initiatives, measure of success and timing to market for your idea.
| 1 | Word Count
Others
| 1 | Word Count
~ End of Page ~